## Project Plan
MO-IT161 - Web Systems and Technology
Gantt Chart of the Team-Selected Web Systems and Technology Project
I. Project Information
| Project Name |  | Tipsy Bean Cafe |  | Project Start Date | 2025-08-28
| Project Development Team |  | Group 10: Santos, Kristien Jaia Virtucio, Eric Jay Rementas, El Jean Vergara, Charley |  | Project End Date | 2025-11-10
II. Project Activities
| Task No | Task Name |  | Task Activities |  | Assigned Member | Start Date | Due Date | Duration (Days) | Percentage of Task Completion | Week | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[11 empty] | Scaffold Activity | Project Initiation |  |  |  |  | Group Project Selection |  |  |  |  | Requirement Analysis |  |  |  |  | Website Design |  |  |  |  | Draft of Milestone 1: Milestone 1 - HTML and CSS Template |  |  |  |  | Milestone 1: Milestone 1 - HTML and CSS Template |  |  |  |  | Milestone 1 Revision Week |  |  |  |  | JavaScript and Bootstrap |  |  |  |  | Draft of Milestone 2: Milestone 2: Interactive Website |  |  |  |  | Milestone 2: Milestone 2: Interactive Website |  |  |  |  | Milestone 2 Revision/Terminal Assessment |  |  |  |  | Terminal Assessment: Project Presentation
[11 empty] | Start Date | 2025-08-27 |  |  |  |  | 2025-09-01 |  |  |  |  | 2025-09-08 |  |  |  |  | 2025-09-15 |  |  |  |  | 2025-09-22 |  |  |  |  | 2025-09-29 |  |  |  |  | 2025-10-06 |  |  |  |  | 2025-10-13 |  |  |  |  | 2025-10-20 |  |  |  |  | 2025-10-27 |  |  |  |  | 2025-11-03 |  |  |  |  | 2025-11-10
[11 empty] | Days | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17
| I. | Project Initiation
| I.I | Form a group and create a Gspace for meetings |  | Includes creating a group folder and assessing initial requirements |  | ALL | 2025-08-28 | 2025-08-31 | 3 | 100%
| I.II | Project Plan |  | Create Gantt Chart using template, customize as needed |  | Rementas | 2025-08-30 | 2025-09-03 | 4 | 100%
Santos
| I.III | Group Meeting |  | Meet on Gspace to discuss roles and project ideas |  | ALL | 2025-09-04 | 2025-09-04 | 0 | 100%
| I.IV | Group Approval |  | Finalize project and start Requirements Gathering Document |  | ALL | 2025-09-04 | 2025-09-04 | 0 | 100%
| 1 | Requirement Analysis
| 1.1 | Define Project Objectives and Scope, Identify Stakeholders |  | • Brainstorm with team to clarify project goals. • Create a project charter outlining objectives and scope. • Identify key stakeholders and their roles in the project. |  | Virtucio | 2025-09-04 | 2025-09-06 | 2 | 100%
| 1.2 |  |  |  |  | Santos
| 1.3 | Document Functional and Non-Functional Requirements |  | Compile a comprehensive list of functional, non-functional, technical, and business requirements based on collected data. |  | Virtucio | 2025-09-05 | 2025-09-06 | 1 | 100%
| 1.4 | Update/revisions of the Document |  | Update new information if available or as project scope changes |  | Virtucio | 2025-09-06 | 2025-09-07 | 1 | 100%
| 1.5 | Finalize Requirements Gathering Document |  | Review the Document |  | Santos | 2025-09-06 | 2025-09-07 | 1 | 100%
| 1.6 | Requirements Gathering |  | Submit document in Camu |  | ALL | 2025-09-08 | 2025-09-08 | 0 | 100%
| 2 | Website Design
| 2.1 | Draft HTML Structure |  | • Identify Key Sections • Determine Additional Elements |  | Virtucio | 2025-09-09 | 2025-09-11 | 2 | 100%
| 2.2 | Wireframe Design |  | Create draft for wireframe |  | Santos | 2025-09-10 | 2025-09-12 | 2 | 100%
Rementas
| 2.3 | Wireframe Finalization |  | Review the wireframe, Revise if necessary |  | ALL | 2025-09-10 | 2025-09-11 | 1 | 100%
| 2.4 | Wireframe Documentation |  | Fill up the Wireframe Justification and Technical Planning Dcocument |  | Virtucio | 2025-09-11 | 2025-09-14 | 3 | 100%
Santos
| 2.5 | Homework: Project Wireframe |  | Submit document in Camu |  | ALL | 2025-09-15 | 2025-09-15 | 0 | 100%
| II. | Milestone 1: Milestone 1 - HTML and CSS Template
| II.I | Create draft for Milestone 1 |  | Build the HTML and CSS template for Tipsy Bean |  | Virtucio | 2025-09-16 | 2025-09-22 | 6 | 100%
| II.II | Week 4: Milestone 1 - HTML and CSS Template (Draft) |  | Submit in Camu |  | ALL | 2025-09-22 | 2025-09-22 | 0 | 100%
| II.III | Milestone 1 Revisions |  | Revise as per feedback |  | Virtucio | 2025-09-23 | 2025-09-28 | 5 | 100%
Santos
| II.IV | Finalize and Submit Milestone 1 |  | Submit in Camu |  | ALL | 2025-09-29 | 2025-09-29 | 0 | 100%
| 3 | Implementing JavaScript and Bootstrap
| 3.1 | Practice |  | Create a Personal Copy of the project to practice JavaScript and Bootstrap |  | ALL | 2025-09-29 | 2025-10-10 | 11 | 100%
| 3.2 | Group Meeting |  | Meet with the team to discuss progress and plans for Milestone 2 |  | ALL | 2025-10-10 | 2025-10-10 | 0 | 100%
| III. | Milestone 2: Interactive Website
| III.I | Create draft for Milestone 2 |  |  |  | ALL | 2025-10-10 | 2025-10-20 | 10 | 100%
| III.III | Revise Milestone 2 |  | According to feedback or consultation |  | ALL | 2025-10-20 | 2025-10-26 | 6 | 100%
| III.IV | Finalize and Submit Milestone 2 |  | Submit in Camu |  | ALL | 2025-10-23 | 2025-10-27 | 4 | 100%
| 4 | Testing Phase
| 4.1 | Create a Test Case Document |  | Share GitHub Repository for testing and test partner group’s work |  | Rementas | 2025-10-27 | 2025-11-05 | 9 | 100%
Vergara
| 4.2 | Conduct the Testing Process |  | Share GitHub Repository for testing and test partner group’s work |  | Virtucio | 2025-11-03 | 2025-11-05 | 2 | 100%
| 4.3 | Revise Web Design |  | According to testing feedback |  | Santos | 2025-11-05 | 2025-11-08 | 3 | 100%
Virtucio
| IV. | Terminal Assessment: Refined and Tested Interactive Website
| IV.I | Create document for TA Draft |  | Begin preparation for the Terminal Assessment |  | Virtucio | 2025-11-01 | 2025-11-08 | 7 | 100%
| IV.II | Finalize Web Design |  | Review and Revise |  | Santos | 2025-11-01 | 2025-11-08 | 7 | 100%
Virtucio
| IV.IV | Project Plan Documentation |  | Update Project Plan |  | Santos | 2025-11-01 | 2025-11-08 | 7 | 100%
| IV.V | TA: Refined and Tested Interactive Website(Draft) |  | Submit in Camu |  | ALL | 2025-11-10 | 2025-11-10 | 0 | 100%
| IV.V | Revise TA |  | If necessary |  | ALL | 2025-11-10 | 2025-11-17 | 7 | 0%
| IV.V | TA: Refined and Tested Interactive Website(Submission) |  | Submit in Camu |  | ALL | 2025-11-17 | 2025-11-17 | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
[9 empty] | 0 | 0%
Formulas:
WEEK 1 = [WEEK 1, row above]
WEEK 2 = [WEEK 2, row above]
WEEK 3 = [WEEK 3, row above]
WEEK 4 = [WEEK 4, row above]
WEEK 5 = [WEEK 5, row above]
WEEK 6 = [WEEK 6, row above]
WEEK 7 = [WEEK 7, row above]
WEEK 8 = [WEEK 8, row above]
WEEK 9 = [WEEK 9, row above]
WEEK 10 = [WEEK 10, row above]
WEEK 11 = [WEEK 11, row above]
WEEK 12 = [WEEK 12, row above]